## Sheet1
Priority |  |  |  |  | Week
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | Progress So Far:
1 | Code User Objects |  | 5 | pts | [6 empty] | 0 | pts
1 | Skeleton Code |  | 3 | pts | [7 empty] | pts
2 | Diagram & notes for records/logic |  | 3 | pts | [7 empty] | pts
2 | Student Record 1.0 back-end |  | 3 | pts | [7 empty] | pts
2 | Student Record 1.0 front-end |  | 1 | pts | [7 empty] | pts
3 | Make New User ADMIN |  | 3 | pts | [7 empty] | pts
3 | Rough Interface |  | 1 | pts | [7 empty] | pts
3 | Code around Print Module |  | 3 | pts | [7 empty] | pts
4 | Modify Records ADMIN |  | 3 | pts | [7 empty] | pts
4 | Student Clock Interface |  | 3 | pts | [7 empty] | pts
4 | Review/Modify In/Out status INSTRUCTOR |  | 1 | pts | [7 empty] | pts
5 | View Reports INSTRUCTOR |  | 3 | pts | [7 empty] | pts
5 | UI 2.0 |  | 3 | pts | [7 empty] | pts
5 | Test-run print module in situ |  | 3 | pts | [7 empty] | pts
6 | Archive |  | 3 | pts | [7 empty] | pts
6 | UI tweaking |  | 1 | pts | [7 empty] | pts
6 | Finalize Code |  | 3 | pts | [7 empty] | pts
[5 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
|  | Estimated |  | Estimated | 8 | 15 | 22 | 29 | 38 | 45
|  | Actual |  | Actual | 0 | 0 | 0 | 0 | 0 | 0
|  | Total |  | Total | 45 | 45 | 45 | 45 | 45 | 45
[11 empty] | 0 |  | 0% | Completed
3 | Make New User ADMIN |  | 3
4 | Modify Records ADMIN |  | 3
4 | Student Clock Interface |  | 3
5 | View Reports INSTRUCTOR |  | 3
4 | Review/Modify In/Out status INSTRUCTOR |  | 1
3 | Rough Interface |  | 1
1 | Code User Objects |  | 5
2 | Diagram & notes for records/logic |  | 3
1 | Skeleton Code |  | 3
3 | Code around Print Module |  | 3
2 | Student Record 1.0 back-end |  | 3
2 | Student Record 1.0 front-end |  | 1
5 | UI 2.0 |  | 3
6 | Archive |  | 3
5 | Test-run print module in situ |  | 3
6 | UI tweaking |  | 1
6 | Finalize Code |  | 3